## Sheet1
Managerial Risks
Risk | Importance | Difficulty | RiskLevel | Techniques for Mitigation Strategy | Addressed
Individual Participation | 4 | 4 | 4 | Keep in constant communication
Team dedication | 3 | 4 | 3.5 | Keep in constant communication, be real clear about when you're not free
Clear Specification | 4 | 2 | 3 | Keep our sponsor on task for creating spec
If we can't rangle Jevin | 2 | 3 | 2.5 | Have our sponsor keep him accountable, be very praiseful in communications
Putting too much pressure on one person | 4 | 1 | 2.5 | Constant work evaluation, be verbal about being tasked too heavily
Do need a way to guage our progress | 3 | 2 | 2.5 | Create issues for everything we do in Redmine
Quality Definition | 3 | 2 | 2.5 | Keep our sponsor on task in putting that in spec
Thinking we have more time than we really do | 3 | 1 | 2 | Set deadlines early
Planning too much up front | 3 | 1 | 2 | Practice Aglie methodoloy, and fail fast
Not planning up front | 1 | 1 | 1 | Practice Aglie methodoloy, and fail fast
Feature creep | 1 | 1 | 1 | Adhering to specification
Sudden growth in requirements | 1 | 1 | 1 | Be ready to say no
Technical Risks
Risk | Importance | Difficulty | RiskLevel | Techniques for Mitigration Strategy | Addressed
Unforseen issues with the algorithms we're using | 4 | 5 | 4.5 | Be clear and reasonable about our limitations
Being unable to understand the algorithms we're using | 4 | 5 | 4.5 | Be clear and reasonable about our limitations
Being able to convert Jevin's algorithm to the paper level | 4 | 4 | 4 | Have a clear understanding of the scope of the algorithm, be clear and reasonable about our limitations
Limitations with the API | 2 | 4 | 3 | Find another another data source, use multiple data sources if necessary
Visualization | 2 | 3 | 2.5 | Utilize work that's been done by others
Differing skillsets | 3 | 2 | 2.5 | Be open and honest about difficulties, ask for help if needed
Stuck with no other source than PubMed | 1 | 1 | 1 | We're currently working on other data sources
Not being able to switch between data sources | 1 | 1 | 1 | We're currently working on other data sources